## Sheet1
Project Delivery Plan - template
RAG | Mid Wales Commercial Property Investment Fund | Start Date | End Date | Duration | Assigned to | Completed
| Open Call Stage | 2025-05-01 | 2025-06-11 | 41
| Viability Stage (RIBA Stage 0) | 2025-06-12 | 2025-08-13 | 62
| Viability Stage Assessment | 2025-08-14 | 2025-09-25 | 42
| Development Stage (RIBA Stages 1 to 3) | 2025-09-26 | 2026-03-12 | 167
| RIBA Stage 1 | 2025-09-26 | 2025-10-23 | 27
| RIBA Stage 2 | 2025-10-24 | 2026-01-15 | 83
| RIBA Stage 3 | 2026-01-16 | 2026-03-12 | 55
| Developed Proposal Work | 2025-09-26 | 2026-03-12 | 167
| Secure Planning Approval | 2026-03-13 | 2026-06-04 | 83
| Development Stage Assessment | 2026-03-13 | 2026-04-24 | 42
| Delivery Stage (RIBA Stages 4 to 6) | 2026-04-27 | 2028-02-25 | 669
| RIBA Stage 4 | 2026-04-27 | 2026-08-14 | 109
| RIBA Stage 5 Construct the Asset | 2026-08-17 | 2028-02-25 | 557
| RIBA Stage 6 | 2027-12-06 | 2028-02-25 | 81
| Post-Completion : Defects Period and Benefits Realisation (RIBA Stage 7) | 2028-02-28 | 2029-01-26 | 333
| Lifecycle (Project Duration) | 2025-05-01 | 2029-01-26 | 1366
| TODAY | 2025-05-20 | 2025-05-20 | 1
Insert additional rows above Lifecycle: |  |  |  |  | MIN | MAX
Once you have amended the Start and End Dates in the above table, select the date axis on the Gantt Chart, followed by the graph symbol on the Format Axis (on the right hand side of your screen), select the Axis Options dropdown and enter the below values into the Minimum, and Maximum bounds field |  |  |  |  | 45778 | 47144
2025-05-20
Formulas:
End Date = MAX(D4:[End Date, row above])